## ProductBackLog
Project Name:Enter_Your_Project_Name Group Members:Member_1,Member_2,Member_3,Member_4,Member_5,Member_6,Member_7
# | Product BackLog
1 | Database Integration
2 | Implement user registration and login system to application through username and password
3 | Allow users to connect smart lights to the system through application
4 | Allow users to control smart lights through the mobile application
5 | Develop an intuitive and user friendly interface
6 | Ensure offline functionality for basic features
7 | Implement object tracking and lost item location system
8 | Blinking lights to indicate lost objects
9 | Integrate the system with smart assistants such as Google Assistant and Alexa to support.
10 | Support voice commands for controlling the lights and locating objects
11 | Create automaticlightning scenarios based on user habits
12 | Implemnt push notifications for system alerts and reminders
13 | Optimize UI performence for better user experience
14 | Implement multi-language support for global accessibility
15 | Optimize database for scalability and efficiency
16 | Encrypt user data and ensure compliance with security standarts
17 | Provide a history log of searched items for frequantly misplaced items
18 | Implement reminders for important items by blinking the lights respectively
19 | Optimize smart lights for mnimal energy consumption to enhance efficiency and sustainability
20 | Ensure full compatibility with IOS and Android devices such as smartphones and tablets

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, PO | Database Integration | Not Started | High | 2025-10-03 | 2025-10-05 | 2 | A robust database is the central, structured repository that efficiently stores, organizes, and secures all critical application data.
Developer | Implement user registration and login system to application through username and password | Not Started | High | 2025-10-05 | 2025-10-10 | 5 | Essential for personalization and data security. Include features like password recovery and two-factor authentication
Developer | Allow users to connect smart lights to the system through application | Not Started | High | 2025-10-10 | 2025-10-15 | 5 | Creates a connection between system and lights
Developer | Allow users to control smart lights through the mobile application | Not Started | High | 2025-10-15 | 2025-10-20 | 5 | Creates a connection between system and user
Developer | Develop an intuitive and user friendly interface | Not Started | High | 2025-10-20 | 2025-10-24 | 4 | Implements the needed attributes to the main screen to improve the functionality
21
BACKLOG
As a user, I want to register with my email address, so that I can access my account, my home assitants and lightning systems.
STATUS: Ready to Start
As a user, I want to match my smart home assistant systems with the application.
STATUS: Ready to Start
Dev
Dev
As a developer, I want to design and plan the database schema so that our data for users, lightning systems, assistant systems, items,item's places is well-structured and scalable.
STATUS: In Progress
PO
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer,SM | Ensure offline functionality for basic features | Not Started | High | 2025-10-24 | 2025-10-26 | 2 | Enable core features (e.g., lighting control, item tracking) to work without internet.
Developer | Implement object tracking and lost item location system | Not Started | High | 2025-10-26 | 2025-11-09 | 14 | A system to track objects and locate lost items using tags or sensors. High user value for convenience.
Developer | Blinking lights to indicate lost objects | Not Started | High | 2025-11-09 | 2025-11-10 | 1 | Use connected lights to blink and guide users to lost items.
Developer | Integrate the system with smart assistants such as Google Assistant and Alexa to support. | Not Started | Medium | 2025-11-10 | 2025-11-11 | 1 | The system should recognize and execute voice commands via Google Assistant and Alexa.
Developer, SM, PO | Support voice commands for controlling the lights and locating objects | Not Started | Medium | 2025-11-11 | 2025-11-13 | 2 | Users should be able to use voice commands to locate their belongings, and the system should respond accordingly.
20
BACKLOG
Formulas:
DURATION (DAYS) = DAYS([FINISH],[START])
As a user, I want to be able to use my systems eventough the internet is gone.
STATUS: Not Started
As a user, I want to be able to use voice commands to use some functions of the system.
STATUS: Not Started
Dev
As a user, I want the system must show me where is my lost objects by blinking onto them.
STATUS: Not Started
Dev
Dev
SM
SM
SM
As a user, I want to connect my other assistant to the system and use them as i want.
STATUS: Not Started
Dev
SM

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, SM | Create automatic lighting scenarios based on user habits. | Not Started | High | 2025-11-13 | 2025-11-16 | 3 | The system should analyze user behavior and patterns to create automated lighting scenarios.
Dev | Implement push notifications for system alerts and reminders. | Not Started | High | 2025-11-16 | 2025-11-17 | 1 | Add push notifications to alert users about system events (e.g., low battery, item found) or reminders, and also user preference settings.
Developer, PO, SM | Optimize UI performance for better user experience. | Not Started | Medium | 2025-11-17 | 2025-11-19 | 2 | Improve the quality
Developer, PO, SM | Implement multi-language support for global accessibility. | Not Started | Medium | 2025-11-19 | 2025-11-24 | 5 | Add translate UI into major languages (e.g., Turkish, English). Ensure UI handles text expansion/contraction.
Developer, SM | Optimize database for scalability and efficiency. | Not Started | Low | 2025-11-24 | 2025-11-26 | 2 | Make it runs/queries faster
13
BACKLOG
Formulas:
DURATION (DAYS) = DAYS([FINISH],[START])
As a user, I want the system to learn my habits and use lightning by my actions.
STATUS: Not Started
As a user, I want to use the system without any bugs and with a better user experience.
STATUS: Not Started
Dev
Dev
PO
As a developer, I want to be able to modify the system without having any trouble with current database.
STATUS: Not Started
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, SM, PO | Encrypt user data and ensure compliance with security standards.Encrypt data at rest and in transit. | Not Started | High | 2025-11-26 | 2025-11-27 | 1 | Ensure compliance with KVKK
Developer, SM | Provide a history log of searched items for frequently misplaced items. | Not Started | High | 2025-11-27 | 2025-11-30 | 3 | The system should maintain a log of previously searched items.
Developer, SM, PO | Implement reminders for important items by blinking the lights respectively | Not Started | High | 2025-11-30 | 2025-12-01 | 1 | Users should be able to set reminders for important items.
Developer, SM | Optimize smart lights for minimal energy consumption to enhance efficiency and sustainability.. | Not Started | Medium | 2025-12-01 | 2025-12-05 | 4 | Users should have an option to enable energy-saving modes with predefined settings.
Developer, SM | Ensure full compatibility with iOS and Android devices such as smartphones and tablets. | Not Started | Low | 2025-12-05 | 2025-12-09 | 4 | Test and optimize the system to work flawlessly across all major mobile platforms.
13
BACKLOG
Formulas:
DURATION (DAYS) = DAYS([FINISH],[START])
As a user, I want to be sure that security of my informations is well designed and secure.
STATUS: Not Started
As a user, I want to ensure full compatibility with iOS and Android devices such as smartphones and tablets so that I can access the application seamlessly on any mobile device.
STATUS: Not Started
Dev
Dev
As a user, I want to view a history log of searched items so that I can easily find frequently misplaced items.
STATUS: Not Started
Dev
SM
SM

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
CATEGORY KEY | PRIORITY KEY | STATUS KEY
Research | High | In Progress
Feature | Medium | Ready to Start
Content | Low | Complete
Task |  | On Hold
Update |  | Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0